## EWNs
EARLY WARNING RISK REGISTER |  | Revision No. = |  |  | Date Revised =
Priority Descriptions
1 | URGENT HIGH PRIORITY. Actions need to be agreed and taken NOW as is or soon will be delaying Completion or increasing Prices &/or Defined Cost.
2 | HIGH PRIORITY. Needs to be resolved at or soon after the next scheduled risk reduction meeting in order to avoid delaying Completion or increasing the Prices &/or Defined Cost.
3 | PRIORITY. A plan of actions need to be put in place or confirmed within the next week in order to avoid delaying Completion or increasing Defined Cost.
4 | LOW PRIORITY. Consideration can be put off for up to a 2 weeks. Needs to be resolved within a month.
5 | VERY LOW PRIORITY. Consideration can be put off for a month or more.
EW No. | Description inc. location | Date | By Which | Priority | Actions | By Whom | When By | Date Action
|  | Notified | Party (E, C or SubC) | (see above) | Note : One action per line. Highlight in red if not done by date. |  |  | Closed Out

## CEN & E's response
Compensation Event Notification (CEN) and Employer's response
[5 empty] | If notified by C |  | If B, last date
CEN No. | From whom | Date | CE no. | Brief Details | E's response | Date | for C's quotation | Relevant other docs
| E or C : Name |  | 60.1 (?) |  | to CEN from C |  | b4 E assesses | Previous | Next
[5 empty] | (A i to iv or B ?) |  | (Column G + 2 weeks)

## CEQ & E's response
Compensation Event Quotation and Employer's response (also covers an Employer's assessment)
E's response
Acceptance (A)
Non-acceptance (N-A)
| Quotation / | Revised | Is this an E's | Date |  |  | If N-A, C to resubmit (RS) | Date of
CE No. | Assessment | quote ? | assessment ? | Received | (Proposed) CHANGE in |  | or E to assess (E2A) OR | Response / | If accepted/E's assessment, new |  | Relevant other docs
(see previous sheet) | Ref. (A, B etc) | (Yes/ No) | (Yes/No) | or Made | Prices | Completion Date | E's assessment (EsA) | E's assesment | Prices | Completion Date | Previous | Next

## Payment Certificates
Certificate | Date | Cumulative |  |  | Cumulative | Change in amount due
No. |  | PWDD | plus | less | Amount Due | / amount certified
0

## OCCF
Other Contractual Communications Form
[5 empty] | Response | If 'Yes'
| From whom |  | Under which |  | Required? | by | Relevant other docs
OCF No. | E or C : Name | Date | clause ? | Details | (Yes / No) | when | Previous | Next

## Defects & Completion
|  |  |  | Notified b4 | If 'Yes',does it need | If 'No', what date must
| From whom |  |  | Completion ? | to be corrected to | it be corrected by | Date
Defect No. | E or C : Name | Date | Details | (Yes / No) | achieve Completion ? | (the date notified + the dcp) | corrected
Insert as a line item the date of Completion i.e. Date, then Completion achieved. If Defects were notified on the Completion Certificate state also 'Defects X to Y notified on Certificate' and list below in normal way.
If a sectional Completion achieved, do same as above, but state section.
From the last date of Completion, add in the line below which states the defects date. The defects date is X weeks after Completion, with 'X' being stated in the Contract Data.
It is typically 52 weeks after Completion and is the last date that the Employer can notify Defects and have them corrected under contract, so put a date in your diary (say 51 weeks from Completion) to have a final inspection !